## 1ST QTR
FDP Form 6 - TRUST FUND UTILIZATION
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1ST QUARTER OF CY 2022
LOCAL GOVERNMENT UNIT - CITY OF SAN FERNANDO, PAMPANGA
Program or Project | Particulars | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
DPWH RO III - SLRF | V. Tiomico St., Sto. Rosario | Sto. Rosario, CSFP | 616217.48 | no data | no data | 100% | 616217.48 |  | Fully Liquidated
| V. Tiomico St., Sto. Rosario |  | 554412.77 | Mar. 11, 2011 | Oct. 13 2011 | 100% | 554412.77 |  | Fully Liquidated
| V. Tiomico St., Sto. Rosario |  | 515066 | no data | no data | 100% | 515066 |  | Fully Liquidated
| Abad Santos St., Vega St., Hilario St. and V Tiomico St., Sto Rosario CSFP |  | 907041 | no data | no data | 100% | 907041 |  | Fully Liquidated
| Abad Santos St., Vega St., Hilario St. and V Tiomico St., Sto Rosario CSFP |  | 907041 | no data | no data | 100% | 907041
DBM RO III (Sen. Manuel Villar) Medical Mission and Purchase of Medicines |  | different barangays of CSFP | 2000000 | 2011 | 2012 | 100% | 2000000 |  | Fully Liquidated
DBM RO III (Sen. Mar Roxas) Medical Assistance to Indigents Patients of JBL |  | different barangays of CSFP | 3000000 | no data | no data | 100% | 3000000 |  | Fully Liquidated
DSWD RO III - National Child Development Center |  | Sindalan, CSFP | 2200000 | no data | no data | 100% | 2200000 |  | Fully Liquidated
|  | Sindalan, CSFP | 452049.66 | no data | no data | 100% | 452049.66 |  | Fully Liquidated
DENR EMB - Solid Waste Management Program | Establishment of MRF | Del Rosario, CSFP | 500000 | no data | no data | 100% | 500000 |  | Fully Liquidated | refund already prepared on 7/29 P72239.00
DENR EMB - Closure and Rehabilitation of LGU Open & Controlled Dump Site | installation of gas vents part of the rehabilitation of former disposal facility at Lara | Lara, CSFP | 3332879.17 | Aug. 25, 2018 | Oct. 3, 2018 | 100% | 3332879.17 |  | Fully Liquidated
DILG RO III - Most Outstanding LGU for Environmental Compliance | Strengthening of enforcement (CENRO) | CSFP | 200000 | no data | no data | 100% | 200000 |  | Fully Liquidated | balance for refund
DSWD RO III-Child Abuse Prevention and Intervention Program (BUB) |  | different barangays of CSFP | 417000 | Sept. 28, 2015 | Oct. 3, 2015 | 100% | 417000 |  | Fully Liquidated
DTI RO III-OBOP (BUB) |  | different barangays of CSFP | 500000 | 2016-05-01 | 2016-09-01 | 100% | 500000 |  | Fully Liquidated
DTI RO III-Yamang Pinoy (BUB) |  | different barangays of CSFP | 500000 | 2015-03-01 | 2015-08-01 | 100% | 500000 |  | Fully Liquidated
DSWD RO III - Supplemental Feeding Program |  | different barangays of CSFP | 4351100 | no data | no data | 100% | 4351100 |  | Fully Liquidated
|  |  | 4466052 | Jan.8, 2016 | no data | 100% | 4466052 |  | Fully Liquidated
|  |  | 7104478 | Jan.3, 2017 | June 30, 2017 | 100% | 7104478 |  | Fully Liquidated
|  |  | 4860000 | Óct. 25, 2021 | 2022-01-31 | 99.89% | 4854750 |  | Project Ongoing
DILG RO III - Performance Challenge Fund | Upgrading of Road from Alasas to Del Rosario | Alasas, CSFP | 3000000 | Sept.23, 2015 | Nov. 21, 2015 | 100% | 3000000 |  | Fully Liquidated
| Construction of Evacuation Center at Civic Center | San Isidro, CSFP | 3400000 | Jan. 5, 2018 | June 3, 2018 | 100% | 3400000 |  | Fully Liquidated
| Construction of Public Child Development Center | Del Pilar, CSFP | 2400000 | June 3, 2018 | Aug. 16, 2018 | 100% | 2400000 |  | Fully Liquidated
|  | Del Pilar, CSFP | 5100000 | June 6, 2019 | Sept. 3, 2019 | 100% | 5100000 |  | Fully Liquidated
| Road from Magliman to Alasas | San Isidro and Alasas, CSFP | 3500000 | June 28, 2020 | Óct. 5, 2020 | 100% | 3500000 |  | Fully Liquidated
DSWD RO III- Bottom Up Budgeting for Construction/Repair of Day Care Centers | San Agustin, Juliana, San Nicolas, Gloria II Sindalan, Sta Lucia, Northville, Malpitic, Maimpis and Pulung Bulu | San Agustin, Juliana, San Nicolas, Sindalan | 3550000 | Mar. 15, 2016 | June 13, 2016 | 100% | 3550000 |  | Fully Liquidated
|  | Northville 14, Maimpis, Malpitic, Pulung Bulu |  | Mar. 21, 2016 | May 20, 2016
|  | Sta Lucia |  | Mar. 21, 2016 | May 20, 2016
DA ROIII-Sustainable Agri-Fisheries Based Livelihood (BUB) |  | different barangays of CSFP | 500000 | 2015-06-01 | 2016-04-01 | 100% | 500000 |  | Fully Liquidated | refund already prepared on 6/28 amounting to P2340
DA ROIII-Farm Mechanization (BUB) |  | different barangays of CSFP | 600000 | 2015-06-01 | 2016-05-01 | 100% | 600000 |  | Fully Liquidated
LGSF-Integrated Community Food Production (BUB) |  | different barangays of CSFP | 500000 | 2016-01-01 | 2016-12-01 | 100% | 500000 |  | Fully Liquidated | ongoing
LGSF-Rehabilitation of BHS (BUB) | Dolores, Magliman, Sta Lucia Mansgold, Sta Lucia, San Nicolas, San Agustin and Northville Malpitic | CSFP | 560000 | Aug. 11, 2016 | Oct. 9, 2016 | 100% | 560000 |  | Fully Liquidated
DOH ROIII-RHU I |  | Dolores, CSFP | 200000 | no data | no data | 100% | 200000 |  | Fully Liquidated
DSWD ROIII-Sustainable Livelihood Program (BUB) |  | different barangays of CSFP | 1457750 | July 27, 2015 | Nov. 10, 2015 | 100% | 1457750 |  | Fully Liquidated | ongoing
|  | different barangays of CSFP | 754000 | Jan. 8, 2018 | Feb. 15, 2018 | 100% | 754000 |  | Fully Liquidated
LGSF-Construction of School Fence (BUB) | Calulut Integrated School, Malpitic Integrated School, Panipuan High School and Pampanga High School | PHS, Calulut, Malpitic & Panipuan IS | 500000 | May 27, 2017 | July 5, 2017 | 100% | 500000 |  | Fully Liquidated
LGSF-Provision of School Furnitures (BUB) |  | different barangays of CSFP | 500000 | 2016 | 2018 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Branding |  | CSFP | 500000 | 2016-07-01 | 2019-03-01 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Brochures / Collaterals |  | CSFP | 500000 | 2016-07-01 | 2018-03-01 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Municipal Site Plan |  | CSFP | 1000000 | 2016-07-01 | 2019-09-01 | 100% | 1000000 |  | Fully Liquidated
DOT-BUB Planning, Production, Development and Marketing |  | CSFP | 600000 | 2016-07-01 | 2018-05-01 | 100% | 600000 |  | Fully Liquidated
DA RO III-Organic Trading Post |  | different barangays of CSFP | 200000 | 2016-09-01 | 2020 | 100% | 200000 |  | Fully Liquidated
|  |  | 300000 | 2015-03-01 | 2015-08-01 | 100% | 300000 |  | Fully Liquidated
|  |  | 1000000 | 2014-01-01 | 2014-07-01 | 100% | 1000000 |  | Fully Liquidated
DA-BUB Combine Harvester |  | different barangays of CSFP | 900000 | 2016-03-01 | 2016-12-01 | 100% | 900000 |  | Fully Liquidated
DA-BUB Power Tiller |  | different barangays of CSFP | 600000 | 2016-03-01 | 2016-12-01 | 100% | 600000 |  | Fully Liquidated
DENR-BUB Barangay Forest Program |  | different barangays of CSFP | 2100000 | 2018-09-01 | 2019-12-01 | 100% | 2100000 |  | Fully Liquidated
DOLE-Child Labor Free Barangay (Nego-Kart) |  | Northville, CSFP | 600000 | 2017-11-01 | Feb.12, 2018 | 100% | 600000 |  | Fully Liquidated
NCCA-Arkitekturang Kapampangan |  | CSFP | 150000 | 2016-04-01 | 2018-10-01 | 100% | 150000 |  | Fully Liquidated
|  |  | 300000 | 2016-04-01 | 2018-10-01 | 100% | 300000 |  | Fully Liquidated
|  |  | 50000 | 2016-04-01 | 2018-10-01 | 100% | 50000 |  | Fully Liquidated
NCCA-Gulis Pamana |  | CSFP | 180000 | 2019-06-01 | 2019-10-01 | 100% | 180000 |  | Fully Liquidated
DTI-BUB Industry Clustering Program |  | CSFP | 600000 | 2016-05-01 | 2017-07-01 | 100% | 600000 |  | Fully Liquidated
DSWD-BUB Protective Services for Solo Parents & Women in Difficult Circumstances |  | different barangays of CSFP | 500000 | 2017-09-01 | 2018-02-01 | 100% | 500000 |  | Fully Liquidated
DSWD-BUB Protective Services for Out-of-School Youth, PWD & Women/ Day Care Parents |  | different barangays of CSFP | 795000 | Sept 26, 2017 | Óct. 6, 2017 | 100% | 795000 |  | Fully Liquidated
DSWD-Child Devt Center Conversion Program |  | 7 different barangays of CSFP | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
DSWD-Devt of Database for Children 0-17 Y/O |  | different barangays of CSFP | 50000 | 2019-07-01 | 2019-12-01 | 94.4% | 47200 |  | Project Ongoing
DSWD-Cash For Work |  | different barangays of CSFP | 3488940 | Apr. 3, 2018 | Apr. 10, 2018 | 100% | 3488940 |  | Fully Liquidated
|  | different barangays of CSFP | 1425000 | Oct. 22, 2018 | Nov. 5, 2018 | 100% | 1425000 |  | Fully Liquidated
Civic Center City Park | Civic Center City Park | San Isidro, CSFP | 11951950 | June 6, 2019 | Oct. 3, 2019 | 100% | 11951950 |  | Fully Liquidated
20% Share In Fire Code Revenues |  | CSFP | 3670024.28 | no data | no data | 83.37% | 3059636 |  | Project Ongoing
PTO Cash Incentive for Child Protection |  | CSFP | 100000 | no data | no data | 92.46% | 92456.25 |  | Project Ongoing
|  |  | 100000 | no data | no data | 0% | 0 |  | Project Ongoing
Town Center River Esplanade Phase I |  | Calulut, CSFP | 17538957 | Sept. 4, 2020 | no data | 100% | 17538957 |  | Fully Liquidated
Town Center River Esplanade Phase II |  | Calulut, CSFP | 17695061 | no data | no data | 0% | 0 |  | Project Ongoing
DSWD-Social Amelioration Program |  | different barangays of CSFP | 241137000 | Ápril 7, 2020 | May 28, 2020 | 100% | 241137000 |  | Fully Liquidated
|  |  | 2944500 | Dec. 14, 2020 | no data | 100% | 2944500 |  | Fully Liquidated
Office of the Civil Defense-Gawad Kalasag Award |  | CSFP | 400000 | June 1, 2020 | no data | 85.02% | 340100 |  | Project Ongoing
Pagcor-Construction of Evacuation/Multi-Purpose Hall at PHS |  | PHS | 37500000 | Nov. 27, 2020 | no data | 99.9% | 37461911.74 |  | Project Ongoing
DOH- ADHP and SRA of Frontliners |  | CSFP | 3928090.91 | no data | no data | 100% | 3928090.91 |  | Fully Liquidated
DBM-DRRMF |  | CSFP | 10410533 | no data | no data | 100% | 10410533 |  | Fully Liquidated
LGSF-DRRAP |  | CSFP | 10255089 | no data | no data | 83.81% | 8595175.8 |  | Project Ongoing
DILG ROIII-cash incentives 2020 Regional Manila Bayani 3rd Placer City Category |  | CSFP | 100000 | no data | no data | 98.8% | 98795.5 |  | Project Ongoing
DOT ROIII-Farm and Gastronomy Tours |  | CSFP | 200500 | no data | no data | 100% | 200500 |  | Fully Liquidated
DOH RO III-Most Improved LGUs in Environmental Health Services |  | CSFP | 100000 | no data | no data | 0% | 0 |  | Project Ongoing
SM Primeholdings-Rehabilitation of Telabastagan Creek |  | Telabastagan, CSFP | 828023.34 | no data | no data | 0% | 0 |  | Project Ongoing
Province of Pampanga-Purchase of Service Vehicle (SP) |  | CSFP | 1400000 | no data | no data | 100% | 1400000 |  | Fully Liquidated
DILG RO III-Bottom Up Budgeting for Disaster Preparedness |  | different barangays of CSFP | 2250000 | no data | no data | 100% | 2250000 |  | Fully Liquidated
|  |  | 250000 | no data | no data | 100% | 250000 |  | Fully Liquidated
Presidential Management Staff (various projects of CSFP) |  | different barangays of CSFP | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
|  |  | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
|  |  | 1000000 | 2006 | 2007 | 100% | 1000000 |  | Fully Liquidated
|  |  | 1000000 | 2007 | 2007 | 100% | 1000000 |  | Fully Liquidated
DBM RO III - OPPSF |  | different barangays of CSFP | 50000000 | 2008 | 2008 | 100% | 50000000 |  | Fully Liquidated
|  |  | 15000000 | 2010 | 2010 | 100% | 15000000 |  | Fully Liquidated
North Luzon Railways, Corp. |  | San Nicolas to Telabastagan, CSFP | 27709118 | 2009 | 2010 | 100% | 27709118 |  | Fully Liquidated
DOLE RO III - DOLE Kabuhayan Nego Kart |  | different barangays of CSFP | 375000 | 2009-11-01 | 2010-02-01 | 100% | 375000 |  | Fully Liquidated
|  |  | 600000 | 2010-11-01 | 2011-02-01 | 100% | 600000 |  | Fully Liquidated
|  |  | 355000 | 2011-05-01 | 2011-08-01 | 100% | 355000 |  | Fully Liquidated
DOLE RO III - DOLE Integrated Livelihood Program |  | different barangays of CSFP | 200000 | 2011-04-01 | 2011-06-01 | 100% | 200000 |  | Fully Liquidated
DILG RO III - Public Transport Assistance Program |  | different barangays of CSFP | 368250 | no data | no data | 100% | 368250 |  | Fully Liquidated
DILG RO III - Gawad Pamana ng Lahi | For Love of Mother Earth, Inc-City's Ecological Solid Waste Management Program (ESWM) | different barangays of CSFP | 2000000 | 2012 | 2013 | 100% | 2000000 |  | Fully Liquidated
| Upgrading and Concreting of Road at Brgy Del Pilar to New Public Market |  | 3000000 | Dec. 3, 2013 | Jan. 21, 2014 | 100% | 3000000 |  | Fully Liquidated
DBM RO III - Rehabilitation /Completion of road network of Regional Center at Maimpis CSFP |  | Maimpis, CSFP | 10000000 | no data | no data | 100% | 10000000 |  | Fully Liquidated
DBM RO III - Rehabilitation /Improvement of Maimpis Creek |  | Maimpis, CSFP | 10000000 | Oct. 16, 2012 | Nov. 23, 2012 | 100% | 10000000 |  | Fully Liquidated
DBM RO III - Asphalt Overlay/Asphalting of Pavement at Poblacion CSFP |  | Sto. Rosario, CSFP | 15000000 | no data | no data | 100% | 15000000 |  | Fully Liquidated
DBM RO III - Construction of Two-Storey Fire Department Building |  | Sto. Rosario, CSFP | 5000000 | Mar. 31, 2012 | June 27, 2012 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Parian Barangay Road, Mexico, Pampanga |  | Mexico, Pampanga | 5000000 | Dec. 7, 2012 | Feb. 5, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Brgy Sto. Niño & Moras, Sto. Tomas, Pampanga |  | Sto. Tomas, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Maniago Barangay Road, Minalin, Pampanga |  | Minalin, Pampanga | 5000000 | Dec. 26, 2012 | Feb. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Balucuc Tabuyuc Road, Apalit, Pampanga |  | Apalit, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Cabetican Barangay Road, Bacolor, Pampanga |  | Bacolor, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at San Pedro 2 Brgy Road to Brgy Sta. Lucia, Magalang, Pampanga |  | Magalang, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Sta. Ana Municipal Road, Pampanga |  | Sta. Ana, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at San Simon Municipal Road, Pampanga |  | San Simon, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Sasmuan Municipal Road, Pampanga |  | Sasmuan, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Arayat Municipal Road, Pampanga |  | Arayat, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Rehabilitation of Balimbing-Del Carmen Creek |  | Del Carmen, CSFP | 20000000 | July 10, 2012 | Dec. 7, 2012 | 100% | 20000000 |  | Fully Liquidated
DSWD RO III - Papsmear Project for Women and Mothers of CSFP |  | different barangays of CSFP | 300000 | no data | no data | 100% | 300000 |  | Fully Liquidated
DBM RO III (Sen. Francis Escudero) - Repair and Rehabilitation of Public Markets |  | Old Public Market, Del Pilar, CSFP | 500000 | Jan. 4, 2016 | Feb. 12, 2016 | 100% | 500000 |  | Fully Liquidated
DBM RO III ( Cong. Oscar S. Rodriguez) - Financial Assistance to various LGUs for the implementation of Social Services |  | different barangays of CSFP | 3500000 | no data | no data | 100% | 3500000 |  | Fully Liquidated
DOST RO III - Upgrading of MRF |  | Del Pilar, CSFP | 170000 | no data | no data | 100% | 170000 |  | Fully Liquidated
DSWD RO III - Improvement of San Pablo Batic Day Care Center funded by BCDA |  | San Pablo DCC, CSFP | 200000 | Jan. 31, 2018 | Mar. 1, 2018 | 100% | 200000 |  | Fully Liquidated
DSWD RO III-Social Pension for Indigent Senior Citizens (BUB) |  | different barangays of CSFP | 499800 | 2014-01-01 | 2014-06-01 | 100% | 499800 |  | Fully Liquidated
DA RO III - Grassroots Participatory Budgeting Process - GPBP |  | different barangays of CSFP | 1000100 | no data | no data | 100% | 1000100 |  | Fully Liquidated
DOLE RO III - Yes Program |  | City College, CSFP | 100000 | no data | no data | 100% | 100000 |  | Fully Liquidated
DBM RO III (Sen. Teofisto Guingona III) - Construction of City College Building Elevator |  | City College, CSFP | 5000000 | Feb. 25, 2013 | Mar.27, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III (Sen. Francis Pangilinan) - Scholarship Program |  | City College, CSFP | 1000000 | no data | no data |  | 1000000 |  | Fully Liquidated
DBM RO III (Sen. Francis Pangilinan) - Priority Development Program |  | City College, CSFP | 500000 | no data | no data | 100% | 500000 |  | Fully Liquidated
DSWD RO III - Katas ng VAT Project |  | different barangays of CSFP | 1306000 | 2011-01-01 | May 23, 2011 | 100% | 1306000 |  | Fully Liquidated
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Certified Correct: |  |  | Certified Correct: |  |  |  | Noted by:
EILEEN A. TULIO |  |  | RIZZEL Y. MANGILIT |  |  |  |  | EDWIN D. SANTIAGO
Acting City Accountant |  |  | OIC-City Budget Officer |  |  |  |  | City Mayor
Note on A68: LGSF
Note on J13: CACCO-Bangs: waiting for credit notice (2/1/17)
Note on J18: CACCO-Bangs: with credit notice
Note on J19: CACCO-Bangs: with credit notice, check for refund still on hand (1/15/17)
Note on J22: CACCO-Bangs: with credit notice

## 2ND QTR
FDP Form 6 - TRUST FUND UTILIZATION
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2ND QUARTER OF CY 2022
LOCAL GOVERNMENT UNIT - CITY OF SAN FERNANDO, PAMPANGA
Program or Project | Particulars | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
DPWH RO III - SLRF | V. Tiomico St., Sto. Rosario | Sto. Rosario, CSFP | 616217.48 | no data | no data | 100% | 616217.48 |  | Fully Liquidated
| V. Tiomico St., Sto. Rosario |  | 554412.77 | Mar. 11, 2011 | Oct. 13 2011 | 100% | 554412.77 |  | Fully Liquidated
| V. Tiomico St., Sto. Rosario |  | 515066 | no data | no data | 100% | 515066 |  | Fully Liquidated
| Abad Santos St., Vega St., Hilario St. and V Tiomico St., Sto Rosario CSFP |  | 907041 | no data | no data | 100% | 907041 |  | Fully Liquidated
| Abad Santos St., Vega St., Hilario St. and V Tiomico St., Sto Rosario CSFP |  | 907041 | no data | no data | 100% | 907041
DBM RO III (Sen. Manuel Villar) Medical Mission and Purchase of Medicines |  | different barangays of CSFP | 2000000 | 2011 | 2012 | 100% | 2000000 |  | Fully Liquidated
DBM RO III (Sen. Mar Roxas) Medical Assistance to Indigents Patients of JBL |  | different barangays of CSFP | 3000000 | no data | no data | 100% | 3000000 |  | Fully Liquidated
DSWD RO III - National Child Development Center |  | Sindalan, CSFP | 2200000 | no data | no data | 100% | 2200000 |  | Fully Liquidated
|  | Sindalan, CSFP | 452049.66 | no data | no data | 100% | 452049.66 |  | Fully Liquidated
DENR EMB - Solid Waste Management Program | Establishment of MRF | Del Rosario, CSFP | 500000 | no data | no data | 100% | 500000 |  | Fully Liquidated | refund already prepared on 7/29 P72239.00
DENR EMB - Closure and Rehabilitation of LGU Open & Controlled Dump Site | installation of gas vents part of the rehabilitation of former disposal facility at Lara | Lara, CSFP | 3332879.17 | Aug. 25, 2018 | Oct. 3, 2018 | 100% | 3332879.17 |  | Fully Liquidated
DILG RO III - Most Outstanding LGU for Environmental Compliance | Strengthening of enforcement (CENRO) | CSFP | 200000 | no data | no data | 100% | 200000 |  | Fully Liquidated | balance for refund
DSWD RO III-Child Abuse Prevention and Intervention Program (BUB) |  | different barangays of CSFP | 417000 | Sept. 28, 2015 | Oct. 3, 2015 | 100% | 417000 |  | Fully Liquidated
DTI RO III-OBOP (BUB) |  | different barangays of CSFP | 500000 | 2016-05-01 | 2016-09-01 | 100% | 500000 |  | Fully Liquidated
DTI RO III-Yamang Pinoy (BUB) |  | different barangays of CSFP | 500000 | 2015-03-01 | 2015-08-01 | 100% | 500000 |  | Fully Liquidated
DSWD RO III - Supplemental Feeding Program |  | different barangays of CSFP | 4351100 | no data | no data | 100% | 4351100 |  | Fully Liquidated
|  |  | 4466052 | Jan.8, 2016 | no data | 100% | 4466052 |  | Fully Liquidated
|  |  | 7104478 | Jan.3, 2017 | June 30, 2017 | 100% | 7104478 |  | Fully Liquidated
|  |  | 4860000 | Óct. 25, 2021 | 2022-01-31 | 100% | 4860000 |  | Fully Liquidated
DILG RO III - Performance Challenge Fund | Upgrading of Road from Alasas to Del Rosario | Alasas, CSFP | 3000000 | Sept.23, 2015 | Nov. 21, 2015 | 100% | 3000000 |  | Fully Liquidated
| Construction of Evacuation Center at Civic Center | San Isidro, CSFP | 3400000 | Jan. 5, 2018 | June 3, 2018 | 100% | 3400000 |  | Fully Liquidated
| Construction of Public Child Development Center | Del Pilar, CSFP | 2400000 | June 3, 2018 | Aug. 16, 2018 | 100% | 2400000 |  | Fully Liquidated
|  | Del Pilar, CSFP | 5100000 | June 6, 2019 | Sept. 3, 2019 | 100% | 5100000 |  | Fully Liquidated
| Road from Magliman to Alasas | San Isidro and Alasas, CSFP | 3500000 | June 28, 2020 | Óct. 5, 2020 | 100% | 3500000 |  | Fully Liquidated
DSWD RO III- Bottom Up Budgeting for Construction/Repair of Day Care Centers | San Agustin, Juliana, San Nicolas, Gloria II Sindalan, Sta Lucia, Northville, Malpitic, Maimpis and Pulung Bulu | San Agustin, Juliana, San Nicolas, Sindalan | 3550000 | Mar. 15, 2016 | June 13, 2016 | 100% | 3550000 |  | Fully Liquidated
|  | Northville 14, Maimpis, Malpitic, Pulung Bulu |  | Mar. 21, 2016 | May 20, 2016
|  | Sta Lucia |  | Mar. 21, 2016 | May 20, 2016
DA ROIII-Sustainable Agri-Fisheries Based Livelihood (BUB) |  | different barangays of CSFP | 500000 | 2015-06-01 | 2016-04-01 | 100% | 500000 |  | Fully Liquidated | refund already prepared on 6/28 amounting to P2340
DA ROIII-Farm Mechanization (BUB) |  | different barangays of CSFP | 600000 | 2015-06-01 | 2016-05-01 | 100% | 600000 |  | Fully Liquidated
LGSF-Integrated Community Food Production (BUB) |  | different barangays of CSFP | 500000 | 2016-01-01 | 2016-12-01 | 100% | 500000 |  | Fully Liquidated | ongoing
LGSF-Rehabilitation of BHS (BUB) | Dolores, Magliman, Sta Lucia Mansgold, Sta Lucia, San Nicolas, San Agustin and Northville Malpitic | CSFP | 560000 | Aug. 11, 2016 | Oct. 9, 2016 | 100% | 560000 |  | Fully Liquidated
DOH ROIII-RHU I |  | Dolores, CSFP | 200000 | no data | no data | 100% | 200000 |  | Fully Liquidated
DSWD ROIII-Sustainable Livelihood Program (BUB) |  | different barangays of CSFP | 1457750 | July 27, 2015 | Nov. 10, 2015 | 100% | 1457750 |  | Fully Liquidated | ongoing
|  | different barangays of CSFP | 754000 | Jan. 8, 2018 | Feb. 15, 2018 | 100% | 754000 |  | Fully Liquidated
LGSF-Construction of School Fence (BUB) | Calulut Integrated School, Malpitic Integrated School, Panipuan High School and Pampanga High School | PHS, Calulut, Malpitic & Panipuan IS | 500000 | May 27, 2017 | July 5, 2017 | 100% | 500000 |  | Fully Liquidated
LGSF-Provision of School Furnitures (BUB) |  | different barangays of CSFP | 500000 | 2016 | 2018 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Branding |  | CSFP | 500000 | 2016-07-01 | 2019-03-01 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Brochures / Collaterals |  | CSFP | 500000 | 2016-07-01 | 2018-03-01 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Municipal Site Plan |  | CSFP | 1000000 | 2016-07-01 | 2019-09-01 | 100% | 1000000 |  | Fully Liquidated
DOT-BUB Planning, Production, Development and Marketing |  | CSFP | 600000 | 2016-07-01 | 2018-05-01 | 100% | 600000 |  | Fully Liquidated
DA RO III-Organic Trading Post |  | different barangays of CSFP | 200000 | 2016-09-01 | 2020 | 100% | 200000 |  | Fully Liquidated
|  |  | 300000 | 2015-03-01 | 2015-08-01 | 100% | 300000 |  | Fully Liquidated
|  |  | 1000000 | 2014-01-01 | 2014-07-01 | 100% | 1000000 |  | Fully Liquidated
DA-BUB Combine Harvester |  | different barangays of CSFP | 900000 | 2016-03-01 | 2016-12-01 | 100% | 900000 |  | Fully Liquidated
DA-BUB Power Tiller |  | different barangays of CSFP | 600000 | 2016-03-01 | 2016-12-01 | 100% | 600000 |  | Fully Liquidated
DENR-BUB Barangay Forest Program |  | different barangays of CSFP | 2100000 | 2018-09-01 | 2019-12-01 | 100% | 2100000 |  | Fully Liquidated
DOLE-Child Labor Free Barangay (Nego-Kart) |  | Northville, CSFP | 600000 | 2017-11-01 | Feb.12, 2018 | 100% | 600000 |  | Fully Liquidated
NCCA-Arkitekturang Kapampangan |  | CSFP | 150000 | 2016-04-01 | 2018-10-01 | 100% | 150000 |  | Fully Liquidated
|  |  | 300000 | 2016-04-01 | 2018-10-01 | 100% | 300000 |  | Fully Liquidated
|  |  | 50000 | 2016-04-01 | 2018-10-01 | 100% | 50000 |  | Fully Liquidated
NCCA-Gulis Pamana |  | CSFP | 180000 | 2019-06-01 | 2019-10-01 | 100% | 180000 |  | Fully Liquidated
DTI-BUB Industry Clustering Program |  | CSFP | 600000 | 2016-05-01 | 2017-07-01 | 100% | 600000 |  | Fully Liquidated
DSWD-BUB Protective Services for Solo Parents & Women in Difficult Circumstances |  | different barangays of CSFP | 500000 | 2017-09-01 | 2018-02-01 | 100% | 500000 |  | Fully Liquidated
DSWD-BUB Protective Services for Out-of-School Youth, PWD & Women/ Day Care Parents |  | different barangays of CSFP | 795000 | Sept 26, 2017 | Óct. 6, 2017 | 100% | 795000 |  | Fully Liquidated
DSWD-Child Devt Center Conversion Program |  | 7 different barangays of CSFP | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
DSWD-Devt of Database for Children 0-17 Y/O |  | different barangays of CSFP | 50000 | 2019-07-01 | 2019-12-01 | 94.4% | 47200 |  | Project Ongoing
DSWD-Cash For Work |  | different barangays of CSFP | 3488940 | Apr. 3, 2018 | Apr. 10, 2018 | 100% | 3488940 |  | Fully Liquidated
|  | different barangays of CSFP | 1425000 | Oct. 22, 2018 | Nov. 5, 2018 | 100% | 1425000 |  | Fully Liquidated
Civic Center City Park | Civic Center City Park | San Isidro, CSFP | 11951950 | June 6, 2019 | Oct. 3, 2019 | 100% | 11951950 |  | Fully Liquidated
20% Share In Fire Code Revenues |  | CSFP | 3670024.28 | no data | no data | 91.65% | 3363676 |  | Project Ongoing
PTO Cash Incentive for Child Protection |  | CSFP | 100000 | no data | no data | 92.46% | 92456.25 |  | Project Ongoing
|  |  | 100000 | no data | no data | 0% | 0 |  | Project Ongoing
Town Center River Esplanade Phase I |  | Calulut, CSFP | 17538957 | Sept. 4, 2020 | no data | 100% | 17538957 |  | Fully Liquidated
Town Center River Esplanade Phase II |  | Calulut, CSFP | 17695061 | no data | no data | 77.33% | 13682716.61 |  | Project Ongoing
DSWD-Social Amelioration Program |  | different barangays of CSFP | 241137000 | Ápril 7, 2020 | May 28, 2020 | 100% | 241137000 |  | Fully Liquidated
|  |  | 2944500 | Dec. 14, 2020 | no data | 100% | 2944500 |  | Fully Liquidated
Office of the Civil Defense-Gawad Kalasag Award |  | CSFP | 400000 | June 1, 2020 | no data | 85.02% | 340100 |  | Project Ongoing
Pagcor-Construction of Evacuation/Multi-Purpose Hall at PHS |  | PHS | 50000000 | Nov. 27, 2020 | no data | 99.88% | 49939998.15 |  | Project Ongoing
DOH- ADHP and SRA of Frontliners |  | CSFP | 3928090.91 | no data | no data | 100% | 3928090.91 |  | Fully Liquidated
DBM-DRRMF |  | CSFP | 10410533 | no data | no data | 100% | 10410533 |  | Fully Liquidated
LGSF-DRRAP |  | CSFP | 10255089 | no data | no data | 83.81% | 8595175.8 |  | Project Ongoing
DILG ROIII-cash incentives 2020 Regional Manila Bayani 3rd Placer City Category |  | CSFP | 100000 | no data | no data | 98.8% | 98795.5 |  | Project Ongoing
DOT ROIII-Farm and Gastronomy Tours |  | CSFP | 200500 | no data | no data | 100% | 200500 |  | Fully Liquidated
DOH RO III-Most Improved LGUs in Environmental Health Services |  | CSFP | 100000 | no data | no data | 0% | 0 |  | Project Ongoing
SM Primeholdings-Rehabilitation of Telabastagan Creek |  | Telabastagan, CSFP | 828023.34 | no data | no data | 0% | 0 |  | Project Ongoing
Province of Pampanga-Purchase of Service Vehicle (SP) |  | CSFP | 1400000 | no data | no data | 100% | 1400000 |  | Fully Liquidated
DILG RO III-Bottom Up Budgeting for Disaster Preparedness |  | different barangays of CSFP | 2250000 | no data | no data | 100% | 2250000 |  | Fully Liquidated
|  |  | 250000 | no data | no data | 100% | 250000 |  | Fully Liquidated
Presidential Management Staff (various projects of CSFP) |  | different barangays of CSFP | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
|  |  | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
|  |  | 1000000 | 2006 | 2007 | 100% | 1000000 |  | Fully Liquidated
|  |  | 1000000 | 2007 | 2007 | 100% | 1000000 |  | Fully Liquidated
DBM RO III - OPPSF |  | different barangays of CSFP | 50000000 | 2008 | 2008 | 100% | 50000000 |  | Fully Liquidated
|  |  | 15000000 | 2010 | 2010 | 100% | 15000000 |  | Fully Liquidated
North Luzon Railways, Corp. |  | San Nicolas to Telabastagan, CSFP | 27709118 | 2009 | 2010 | 100% | 27709118 |  | Fully Liquidated
DOLE RO III - DOLE Kabuhayan Nego Kart |  | different barangays of CSFP | 375000 | 2009-11-01 | 2010-02-01 | 100% | 375000 |  | Fully Liquidated
|  |  | 600000 | 2010-11-01 | 2011-02-01 | 100% | 600000 |  | Fully Liquidated
|  |  | 355000 | 2011-05-01 | 2011-08-01 | 100% | 355000 |  | Fully Liquidated
DOLE RO III - DOLE Integrated Livelihood Program |  | different barangays of CSFP | 200000 | 2011-04-01 | 2011-06-01 | 100% | 200000 |  | Fully Liquidated
DILG RO III - Public Transport Assistance Program |  | different barangays of CSFP | 368250 | no data | no data | 100% | 368250 |  | Fully Liquidated
DILG RO III - Gawad Pamana ng Lahi | For Love of Mother Earth, Inc-City's Ecological Solid Waste Management Program (ESWM) | different barangays of CSFP | 2000000 | 2012 | 2013 | 100% | 2000000 |  | Fully Liquidated
| Upgrading and Concreting of Road at Brgy Del Pilar to New Public Market |  | 3000000 | Dec. 3, 2013 | Jan. 21, 2014 | 100% | 3000000 |  | Fully Liquidated
DBM RO III - Rehabilitation /Completion of road network of Regional Center at Maimpis CSFP |  | Maimpis, CSFP | 10000000 | no data | no data | 100% | 10000000 |  | Fully Liquidated
DBM RO III - Rehabilitation /Improvement of Maimpis Creek |  | Maimpis, CSFP | 10000000 | Oct. 16, 2012 | Nov. 23, 2012 | 100% | 10000000 |  | Fully Liquidated
DBM RO III - Asphalt Overlay/Asphalting of Pavement at Poblacion CSFP |  | Sto. Rosario, CSFP | 15000000 | no data | no data | 100% | 15000000 |  | Fully Liquidated
DBM RO III - Construction of Two-Storey Fire Department Building |  | Sto. Rosario, CSFP | 5000000 | Mar. 31, 2012 | June 27, 2012 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Parian Barangay Road, Mexico, Pampanga |  | Mexico, Pampanga | 5000000 | Dec. 7, 2012 | Feb. 5, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Brgy Sto. Niño & Moras, Sto. Tomas, Pampanga |  | Sto. Tomas, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Maniago Barangay Road, Minalin, Pampanga |  | Minalin, Pampanga | 5000000 | Dec. 26, 2012 | Feb. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Balucuc Tabuyuc Road, Apalit, Pampanga |  | Apalit, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Cabetican Barangay Road, Bacolor, Pampanga |  | Bacolor, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at San Pedro 2 Brgy Road to Brgy Sta. Lucia, Magalang, Pampanga |  | Magalang, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Sta. Ana Municipal Road, Pampanga |  | Sta. Ana, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at San Simon Municipal Road, Pampanga |  | San Simon, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Sasmuan Municipal Road, Pampanga |  | Sasmuan, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Arayat Municipal Road, Pampanga |  | Arayat, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Rehabilitation of Balimbing-Del Carmen Creek |  | Del Carmen, CSFP | 20000000 | July 10, 2012 | Dec. 7, 2012 | 100% | 20000000 |  | Fully Liquidated
DSWD RO III - Papsmear Project for Women and Mothers of CSFP |  | different barangays of CSFP | 300000 | no data | no data | 100% | 300000 |  | Fully Liquidated
DBM RO III (Sen. Francis Escudero) - Repair and Rehabilitation of Public Markets |  | Old Public Market, Del Pilar, CSFP | 500000 | Jan. 4, 2016 | Feb. 12, 2016 | 100% | 500000 |  | Fully Liquidated
DBM RO III ( Cong. Oscar S. Rodriguez) - Financial Assistance to various LGUs for the implementation of Social Services |  | different barangays of CSFP | 3500000 | no data | no data | 100% | 3500000 |  | Fully Liquidated
DOST RO III - Upgrading of MRF |  | Del Pilar, CSFP | 170000 | no data | no data | 100% | 170000 |  | Fully Liquidated
DSWD RO III - Improvement of San Pablo Batic Day Care Center funded by BCDA |  | San Pablo DCC, CSFP | 200000 | Jan. 31, 2018 | Mar. 1, 2018 | 100% | 200000 |  | Fully Liquidated
DSWD RO III-Social Pension for Indigent Senior Citizens (BUB) |  | different barangays of CSFP | 499800 | 2014-01-01 | 2014-06-01 | 100% | 499800 |  | Fully Liquidated
DA RO III - Grassroots Participatory Budgeting Process - GPBP |  | different barangays of CSFP | 1000100 | no data | no data | 100% | 1000100 |  | Fully Liquidated
DOLE RO III - Yes Program |  | City College, CSFP | 100000 | no data | no data | 100% | 100000 |  | Fully Liquidated
DBM RO III (Sen. Teofisto Guingona III) - Construction of City College Building Elevator |  | City College, CSFP | 5000000 | Feb. 25, 2013 | Mar.27, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III (Sen. Francis Pangilinan) - Scholarship Program |  | City College, CSFP | 1000000 | no data | no data |  | 1000000 |  | Fully Liquidated
DBM RO III (Sen. Francis Pangilinan) - Priority Development Program |  | City College, CSFP | 500000 | no data | no data | 100% | 500000 |  | Fully Liquidated
DSWD RO III - Katas ng VAT Project |  | different barangays of CSFP | 1306000 | 2011-01-01 | May 23, 2011 | 100% | 1306000 |  | Fully Liquidated
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
Certified Correct: |  |  | Certified Correct: |  |  |  | Noted by:
RIZZEL Y. MANGILIT |  |  | EILEEN A. TULIO |  |  |  |  | EDWIN D. SANTIAGO
OIC-City Budget Officer |  |  | Acting City Accountant |  |  |  |  | City Mayor
Note on A68: LGSF
Note on J13: CACCO-Bangs: waiting for credit notice (2/1/17)
Note on J18: CACCO-Bangs: with credit notice
Note on J19: CACCO-Bangs: with credit notice, check for refund still on hand (1/15/17)
Note on J22: CACCO-Bangs: with credit notice