## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION III - CENTRAL LUZON |  | CALENDAR YEAR: | 2023
PROVINCE: | PAMPANGA |  | QUARTER: | 2
CITY/MUNICIPALITY: | CITY OF SAN FERNANDO (Capital)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Primary Health Care Facilities (Super RHU) | Citywide | 6300000 | January 2023 | December 2023 | 0% | 0 |  | On-going
Economic Development (pls list down specific projects)
Farm Mechanization Program | Different Brangays | 3500000 | January 2023 | May 2023 | 0% | 0 |  | Sprinkler Irrigation System & Solar Power Irrigation System for Delivery ( Target Date July 2023
Small Farm Mechanization Program | Different Brangays | 2500000 | January 2023 | May 2023 | 99.74% | 2493470 |  | -
Provision of irrigation Facilities | Different Brangays | 1000000 | January 2023 | May 2023 | 99.99% | 999940 |  | -
Upgrading/provision of tools and equipment for the CEO maintenance unit (tree trimming, electrical works, waterways clean-up, carpentry works and others) | - | 10000000 | - | - | 99.8% | 9980000 |  | Release of fund is on the 4th Quarter
Enhance Productivity of Agricultural Land | Different Brangays | 2000000 | January 2023 | September 2023 | 42.71% | 854210 |  | Green Thumb Nursery for approval BAC RESO AWARD, Vegetable Seeds for Delivery
Animal Dispersal | Different Brangays | 1000000 | January 2023 | May 2023 | 96.74% | 967410 |  | For Delivery Horses (Target Date: July 10, 2023 )
Construction and/or Rehabilitation of Roads and Bridges
Improvement/Construction of Road at Bulaon, City of San Fernando, Pampanga | Bulaon | 5000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road (Asphalt Overlay) at Del Carmen, City of San Fernando, Pampanga | Del Carmen | 5000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at Del Pilar, City of San Fernando, Pampanga | Del Pilar | 6000000 | - | - | 99.58% | 5975021.48 |  | Completed
Construction of Road at Dela Paz Norte, City of San Fernando, Pampanga | Dela Paz Norte | 3000000 | Apr 24, 2023 | Jul 22, 2023 | 99.5% | 2984860.77 |  | Completed- May 20, 2023
Improvement/Construction of Road at Lara, City of San Fernando, Pampanga | Lara | 3000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at Magliman, City of San Fernando, Pampanga | Magliman | 5000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at Panipuan, City of San Fernando, Pampanga | Panipuan | 3000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at San Agustin, City of San Fernando, Pampanga | San Agustin | 3000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at San Felipe, City of San Fernando, Pampanga | San Felipe | 3000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at San Pedro, City of San Fernando, Pampanga | San Pedro | 5000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road (Asphalt Overlay) at San Isidro, City of San Fernando, Pampanga | San Isidro | 5000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at Sitio Bulusan to Sitio Balagtas, San Nicolas, City of San Fernando, Pampanga | San Nicolas | 3000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at Sto. Nino, City of San Fernando, Pampanga | Sto. Nino | 3000000 | - | - | 0% | 0 |  | NO NTP
Construction of Road (Pathways/Pavers) along San Fernando River | Along San Fernando River | 5000000 | - | - | 0% | 0 |  | NO NTP
Rehabilitation/Improvement of Road at V. Tiomico St., City of San Fernando, Pampanga | V. Tiomico St., Sto. Rosario | 5000000 | March 31, 2023 | July 8, 2023 | 99.49% | 4974444.6 |  | Completed- June 16, 2023
Improvement/Construction of Road at San Jose, City of San Fernando, Pampanga | San Jose | 5000000 | - | - | 0% | 0 |  | NO NTP
Improvement/Construction of Road at Malino, City of San Fernando, Pampanga | Malino | 3000000 | - | - | 99.47% | 2984038.57 |  | Completed- May 19, 2023
Improvement/Construction of Road at Dolores, City of San Fernando, Pampanga | Dolores | 3000000 | March 25, 2023 | July 12, 2023 | 99.47% | 2984038.57 |  | Completed- May 19, 2023
Improvement/Construction of Road at Duplex, San Isidro, City of San Fernando, Pampanga | San Isidro | 3000000 | May 3, 2023 | Jul 31, 2023 | 99.5% | 2984865.1 |  | Completed
Construction/Improvement of Roads within City of San Fernando, Pampanga | City of San Fernando | 6313485.2 | - | - | 0% | 0 |  | NO NTP
Installation of Solar Studs along McArcthur Hi-way within the City of San Fernando, Pampanga | City of San Fernando | 14063934.77 | - | - | 0% | 0 |  | -
Aid to Barangay Priotity Projects
Brgy. Alasas, CSFP
Installation of Solar lights (streetlights brgy. Wide) | Brgy. Alasas, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Baliti, CSFP
Road widening at purok 1.3.4 | Brgy. Baliti, CSFP | 200000 | July 2023 | December 2023 | 0% | 0 |  | Allotment release on 4th Quarter
Brgy. Bulaon, CSP
Desilting of Line Canal Bulaon Resettlement | Brgy. Bulaon, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Calulut, CSFP
Construction/Rehabilitation of Line Canals in Northville 14 | Brgy. Calulut, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Del Carmen, CSFP
Rehabilitation of Line Canal at Sitio Mauli | Brgy. Del Carmen, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Del Pilar, CSFP
Installation/rehabilitation of Street lighting System in Sitio Paralaya | Brgy. Del Pilar, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Del Rosario, CSFP
Construction of Pavement at Purok 4 | Brgy. Del Rosario, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Dela Paz Norte, CSFP
Construction/Rehabilitation of Pathways/Pavements/Sidewalk situated at Purok 1,2 and 3 | Brgy. Dela Paz Norte, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Dela Paz Sur, CSFP
Installation of Street Lights Solar Panel (Barangay Wide) | Brgy. Dela Paz Sur, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Dolores, CSFP
Installation of CCTV | Brgy. Dolores, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Juliana, CSFP
Fabrication/construction/installation of canal covers in a portion of Purok 5 | Brgy. Juliana, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Lara, CSFP
Purok signaged 1-7 at welcome ark | Brgy. Lara, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Lourdes, CSFP
Desilting/Declogging of Creek Along Malvar Street, Arellano Street, Lapu-Lapu Street, Tandang Sora Street and A. Ruiz Street | Brgy. Lourdes, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Magliman, CSFP
Construction/Rehabilitation of Lined Canal in Purok 4 | Brgy. Magliman, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Maimpis, CSFP
Rehabilitation/Repair of Canal with Cover in Purok 2 St. Claire Subdivision | Brgy. Maimpis, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Malino, CSFP
Improvement of Public Address System | Brgy. Malino, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Malpitic, CSFP
Barangay Wide Construction of Drainage System Line Canal with Cover | Brgy. Malpitic, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Pandaras, CSFP
Rehabilitation & Construction of Lined Canal at Ebus Compound, Fajardo Compound and Guinto Compound | Brgy. Pandaras, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Panipuan, CSFP
Concreting of road at Purok 1 | Brgy. Panipuan, CSFP | 200000 | July 2022 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Pulung Bulu, CSFP
Construction of Line Canal at Purok 4 | Brgy. Pulung Bulu, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Quebiawan CSFP
Repair & Maintenance of Barangay Street Lights/Lamp Post | Brgy. Quebiawan, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Saguin, CSFP
Additional Installtion of Public Address System | Brgy. Saguin, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. San Agustin, CSFP
Rehabilitation of Canal at Sitio Boulevard | Brgy. San Agustin, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. San Felipe, CSFP
Installation of CCTV | Brgy. San Felipe, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. San Isidro, CSFP
Installation of CCTV | Brgy. San Isidro, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. San Jose, CSFP
Improvement and Rehabilitation of Multi Purpose Hall at Purok 5 | Brgy. San Jose, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. San Juan, CSFP
Construction of Drainage Lined Canal with Cover at Purok 7, Sto. Niño Village | Brgy. San Juan, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. San Nicolas, CSFP
Desilting and declogging of canals within the area of Barangay San Nicolas | Brgy. San Nicolas, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. San Pedro, CSFP
Construction of canal cover at Purok 5 | Brgy. San Pedro, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Sta. Lucia, CSFP
Construction of Drainage System Line Canal with Cover at Purok 14 | Brgy. Sta. Lucia, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Santa Teresita, CSFP
Desilting and declogging of waterways | Brgy. Sta. Teresita, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Sto. NIño, CSFP
Construction of Line Canals and Concreting of Road at Jupiter St. | Brgy. Sto. Niño, CFSP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Sto. Rosario, CSFP
Improvement of Pathway at B. Mendoza St. | Brgy. Sto. Rosario, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Sindalan, CSFP
Rehabilitation and improvement of public park at Sindalan Sports Complex | Brgy. Sindalan, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Brgy. Telabastagan, CSFP
Installation of Streetlights | Brgy. Telabastagan, CSFP | 200000 | July 2023 | December 2023 | 0% |  |  | Allotment release on 4th Quarter
Loan Amortization | N/A | 50000000 | January 2023 | December 2023 | 34.37% | 17187094.36 |  | On-going
Environmental Management (pls list down specific projects)
Effective Garbage Collections & Disposal System | Motorpool Compound | 12000000 | January 2023 | June 2023 | 0% |  |  | BAC Resoltuion Approval (Award). Waiting for NTP and PO
Improvement of the Central Materials Recovery Facility - purchase of materials, equipment and operating expenses | Brgy. Lara, CSFP | 8300000 | January 2023 | June 2023 | 0% |  |  | For PR 3rd quarter
Improvement of the Central Materials Recovery Facility (Gardening/Park Development) | Brgy. Lara, CSFP | 5000000 | July 2023 | December 2023 | 0% |  |  | For PR 3rd quarter
Establishment of Botanical Garden, Mini Forest and People's Park | Brgy. Lara, CSFP | 5000000 | July 2023 | December 2023 | 0% |  |  | For PR 3rd quarter
Flood Control
Construction/Improvement of Lined Canal at San Pedro, City of San Fernando, Pampanga | San Pedro | 2000000 | - | - | 99.45% | 1988954.58 |  | Completed- May 17, 2023
Construction/Improvement of Lined Canal at Calulut, City of San Fernando, Pampanga | Calulut | 2000000 | - | - | 99.45% | 1988954.58 |  | Completed- May 30, 2023
Construction/Improvement of Lined Canal at Del Rosario, City of San Fernando, Pampanga | Del Rosario | 2000000 | - | - | 99.46% | 1989227.02 |  | Completed
Construction/Improvement of Lined Canal at Dela Paz Sur, City of San Fernando, Pampanga | Dela Paz Sur | 2000000 | - | - | 99.21% | 1984203.73 |  | Completed
Construction/Improvement of Lined Canal at Dolores, City of San Fernando, Pampanga | Dolores | 10000000 | - | - | 0% |  |  | NO NTP
Construction/Improvement of Lined Canal at Maimpis, City of San Fernando, Pampanga | Maimpis | 2000000 | - | - | 99.5% | 1989985.51 |  | -
Construction/Improvement of Lined Canal at Purok 1, Malpitic, City of San Fernando, Pampanga | Malpitic | 2000000 | - | - | 99.51% | 1990263.14 |  | -
Construction/Improvement of Lined Canal at San Jose, City of San Fernando, Pampanga | San Jose | 2000000 | - | - | 99.56% | 1991296.67 |  | -
Construction/Improvement of Lined Canal with cover at Sitio Bulusan, San Nicolas, City of San Fernando, Pampanga | San Nicolas | 2000000 | - | - | 99.44% | 1988705.94 |  | Completed- May 26, 2023
Construction/Improvement of Lined Canal at Purok 8, Sta. Lucia, City of San Fernando, Pampanga | Sta. Lucia | 2000000 | - | - | 99% | 1979968.1 |  | Completed
Clearing, Desilting and Declogging of Waterways at San Pedro Creek, City of San Fernando, Pampanga | San Pedro | 2000000 | - | - | 99.49% | 1989818.31 |  | Completed- May 16, 2023
Construction of Slope Protection at San Isidro, City of San Fernando, Pampanga | San Isidro | 5000000 | - | - | 99.49% | 4974505.8 |  | -
TOTAL |  | 244977419.97 |  |  |  | 80225276.83
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| RIZZEL Y. MANGILIT |  |  |  | HON. VILMA B. CALUAG
| Acting City Budget Officer I |  |  |  | City Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2