## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: III |  |  | CALENDAR YEAR: | 2023
PROVINCE: PAMPANGA |  |  | QUARTER: | 3
CITY/MUNICIPALITY: CITY OF SAN FERNANDO
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DPWH RO III - SLRF | Sto. Rosario, CSFP | 616217.48 | no data | no data | 100% | 616217.48 |  | Fully Liquidated
|  | 554412.77 | Mar. 11, 2011 | Oct. 13 2011 | 100% | 554412.77 |  | Fully Liquidated
|  | 515066 | no data | no data | 100% | 515066 |  | Fully Liquidated
|  | 907041 | no data | no data | 100% | 907041 |  | Fully Liquidated
|  | 907041 | no data | no data | 100% | 907041
DBM RO III (Sen. Manuel Villar) Medical Mission and Purchase of Medicines | different barangays of CSFP | 2000000 | 2011 | 2012 | 100% | 2000000 |  | Fully Liquidated
DBM RO III (Sen. Mar Roxas) Medical Assistance to Indigents Patients of JBL | different barangays of CSFP | 3000000 | no data | no data | 100% | 3000000 |  | Fully Liquidated
DSWD RO III - National Child Development Center | Sindalan, CSFP | 2200000 | no data | no data | 100% | 2200000 |  | Fully Liquidated
| Sindalan, CSFP | 452049.66 | no data | no data | 100% | 452049.66 |  | Fully Liquidated
DENR EMB - Solid Waste Management Program | Del Rosario, CSFP | 500000 | no data | no data | 100% | 500000 |  | Fully Liquidated
DENR EMB - Closure and Rehabilitation of LGU Open & Controlled Dump Site | Lara, CSFP | 3332879.17 | Aug. 25, 2018 | Oct. 3, 2018 | 100% | 3332879.17 |  | Fully Liquidated
DILG RO III - Most Outstanding LGU for Environmental Compliance | CSFP | 200000 | no data | no data | 100% | 200000 |  | Fully Liquidated
DSWD RO III-Child Abuse Prevention and Intervention Program (BUB) | different barangays of CSFP | 417000 | Sept. 28, 2015 | Oct. 3, 2015 | 100% | 417000 |  | Fully Liquidated
DTI RO III-OBOP (BUB) | different barangays of CSFP | 500000 | 2016-05-01 | 2016-09-01 | 100% | 500000 |  | Fully Liquidated
DTI RO III-Yamang Pinoy (BUB) | different barangays of CSFP | 500000 | 2015-03-01 | 2015-08-01 | 100% | 500000 |  | Fully Liquidated
DSWD RO III - Supplemental Feeding Program | different barangays of CSFP | 4351100 | no data | no data | 100% | 4351100 |  | Fully Liquidated
|  | 4466052 | Jan.8, 2016 | no data | 100% | 4466052 |  | Fully Liquidated
|  | 7104478 | Jan.3, 2017 | June 30, 2017 | 100% | 7104478 |  | Fully Liquidated
|  | 4860000 | Óct. 25, 2021 | 2022-01-31 | 100% | 4860000 |  | Fully Liquidated
DILG RO III - Performance Challenge Fund | Alasas, CSFP | 3000000 | Sept.23, 2015 | Nov. 21, 2015 | 100% | 3000000 |  | Fully Liquidated
| San Isidro, CSFP | 3400000 | Jan. 5, 2018 | June 3, 2018 | 100% | 3400000 |  | Fully Liquidated
| Del Pilar, CSFP | 2400000 | June 3, 2018 | Aug. 16, 2018 | 100% | 2400000 |  | Fully Liquidated
| Del Pilar, CSFP | 5100000 | June 6, 2019 | Sept. 3, 2019 | 100% | 5100000 |  | Fully Liquidated
| San Isidro and Alasas, CSFP | 3500000 | June 28, 2020 | Óct. 5, 2020 | 100% | 3500000 |  | Fully Liquidated
DSWD RO III- Bottom Up Budgeting for Construction/Repair of Day Care Centers | San Agustin, Juliana, San Nicolas, Sindalan | 3550000 | Mar. 15, 2016 | June 13, 2016 | 100% | 3550000 |  | Fully Liquidated
| Northville 14, Maimpis, Malpitic, Pulung Bulu |  | Mar. 21, 2016 | May 20, 2016
| Sta Lucia |  | Mar. 21, 2016 | May 20, 2016
DA ROIII-Sustainable Agri-Fisheries Based Livelihood (BUB) | different barangays of CSFP | 500000 | 2015-06-01 | 2016-04-01 | 100% | 500000 |  | Fully Liquidated
DA ROIII-Farm Mechanization (BUB) | different barangays of CSFP | 600000 | 2015-06-01 | 2016-05-01 | 100% | 600000 |  | Fully Liquidated
LGSF-Integrated Community Food Production (BUB) | different barangays of CSFP | 500000 | 2016-01-01 | 2016-12-01 | 100% | 500000 |  | Fully Liquidated
LGSF-Rehabilitation of BHS (BUB) | CSFP | 560000 | Aug. 11, 2016 | Oct. 9, 2016 | 100% | 560000 |  | Fully Liquidated
DOH ROIII-RHU I | Dolores, CSFP | 200000 | no data | no data | 100% | 200000 |  | Fully Liquidated
DSWD ROIII-Sustainable Livelihood Program (BUB) | different barangays of CSFP | 1457750 | July 27, 2015 | Nov. 10, 2015 | 100% | 1457750 |  | Fully Liquidated
| different barangays of CSFP | 754000 | Jan. 8, 2018 | Feb. 15, 2018 | 100% | 754000 |  | Fully Liquidated
LGSF-Construction of School Fence (BUB) | PHS, Calulut, Malpitic & Panipuan IS | 500000 | May 27, 2017 | July 5, 2017 | 100% | 500000 |  | Fully Liquidated
LGSF-Provision of School Furnitures (BUB) | different barangays of CSFP | 500000 | 2016 | 2018 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Branding | CSFP | 500000 | 2016-07-01 | 2019-03-01 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Brochures / Collaterals | CSFP | 500000 | 2016-07-01 | 2018-03-01 | 100% | 500000 |  | Fully Liquidated
DOT-BUB Municipal Site Plan | CSFP | 1000000 | 2016-07-01 | 2019-09-01 | 100% | 1000000 |  | Fully Liquidated
DOT-BUB Planning, Production, Development and Marketing | CSFP | 600000 | 2016-07-01 | 2018-05-01 | 100% | 600000 |  | Fully Liquidated
DA RO III-Organic Trading Post | different barangays of CSFP | 200000 | 2016-09-01 | 2020 | 100% | 200000 |  | Fully Liquidated
|  | 300000 | 2015-03-01 | 2015-08-01 | 100% | 300000 |  | Fully Liquidated
|  | 1000000 | 2014-01-01 | 2014-07-01 | 100% | 1000000 |  | Fully Liquidated
DA-BUB Combine Harvester | different barangays of CSFP | 900000 | 2016-03-01 | 2016-12-01 | 100% | 900000 |  | Fully Liquidated
DA-BUB Power Tiller | different barangays of CSFP | 600000 | 2016-03-01 | 2016-12-01 | 100% | 600000 |  | Fully Liquidated
DENR-BUB Barangay Forest Program | different barangays of CSFP | 2100000 | 2018-09-01 | 2019-12-01 | 100% | 2100000 |  | Fully Liquidated
DOLE-Child Labor Free Barangay (Nego-Kart) | Northville, CSFP | 600000 | 2017-11-01 | Feb.12, 2018 | 100% | 600000 |  | Fully Liquidated
NCCA-Arkitekturang Kapampangan | CSFP | 150000 | 2016-04-01 | 2018-10-01 | 100% | 150000 |  | Fully Liquidated
|  | 300000 | 2016-04-01 | 2018-10-01 | 100% | 300000 |  | Fully Liquidated
|  | 50000 | 2016-04-01 | 2018-10-01 | 100% | 50000 |  | Fully Liquidated
NCCA-Gulis Pamana | CSFP | 180000 | 2019-06-01 | 2019-10-01 | 100% | 180000 |  | Fully Liquidated
DTI-BUB Industry Clustering Program | CSFP | 600000 | 2016-05-01 | 2017-07-01 | 100% | 600000 |  | Fully Liquidated
DSWD-BUB Protective Services for Solo Parents & Women in Difficult Circumstances | different barangays of CSFP | 500000 | 2017-09-01 | 2018-02-01 | 100% | 500000 |  | Fully Liquidated
DSWD-BUB Protective Services for Out-of-School Youth, PWD & Women/ Day Care Parents | different barangays of CSFP | 795000 | Sept 26, 2017 | Óct. 6, 2017 | 100% | 795000 |  | Fully Liquidated
DSWD-Child Devt Center Conversion Program | 7 different barangays of CSFP | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
DSWD-Devt of Database for Children 0-17 Y/O | different barangays of CSFP | 50000 | 2019-07-01 | 2019-12-01 | 94.4% | 47200 |  | Project Ongoing
DSWD-Cash For Work | different barangays of CSFP | 3488940 | Apr. 3, 2018 | Apr. 10, 2018 | 100% | 3488940 |  | Fully Liquidated
| different barangays of CSFP | 1425000 | Oct. 22, 2018 | Nov. 5, 2018 | 100% | 1425000 |  | Fully Liquidated
Civic Center City Park | San Isidro, CSFP | 11951950 | June 6, 2019 | Oct. 3, 2019 | 100% | 11951950 |  | Fully Liquidated
20% Share In Fire Code Revenues | CSFP | 12062185.35 | no data | no data | 29.54% | 3563216 |  | Project Ongoing
PTO Cash Incentive for Child Protection | CSFP | 300000 | no data | no data | 77.32% | 231956.25 |  | Project Ongoing
Town Center River Esplanade Phase I | Calulut, CSFP | 17538957 | Sept. 4, 2020 | no data | 100% | 17538957 |  | Fully Liquidated
Town Center River Esplanade Phase II | Calulut, CSFP | 17695061 | no data | no data | 100% | 17695061 |  | Fully Liquidated
DSWD-Social Amelioration Program | different barangays of CSFP | 241137000 | Ápril 7, 2020 | May 28, 2020 | 100% | 241137000 |  | Fully Liquidated
|  | 2944500 | Dec. 14, 2020 | no data | 100% | 2944500 |  | Fully Liquidated
Office of the Civil Defense-Gawad Kalasag Award | CSFP | 400000 | June 1, 2020 | no data | 85.02% | 340100 |  | Project Ongoing
Pagcor-Construction of Evacuation/Multi-Purpose Hall at PHS | PHS | 50000000 | Nov. 27, 2020 | no data | 99.88% | 49939998.15 |  | Project Completed
DOH- ADHP and SRA of Frontliners | CSFP | 3928090.91 | no data | no data | 100% | 3928090.91 |  | Fully Liquidated
DBM-DRRMF | CSFP | 10410533 | no data | no data | 100% | 10410533 |  | Fully Liquidated
LGSF-DRRAP | CSFP | 10255089 | no data | no data | 100% | 10255089 |  | Fully Liquidated
DILG ROIII-cash incentives 2020 Regional Manila Bayani 3rd Placer City Category | CSFP | 100000 | no data | no data | 98.8% | 98795.5 |  | Project Ongoing
| CSFP | 100000 | no data | no data | 0% | 0 |  | Project Ongoing
DOT ROIII-Farm and Gastronomy Tours | CSFP | 200500 | no data | no data | 100% | 200500 |  | Fully Liquidated
DOH RO III-Most Improved LGUs in Environmental Health Services | CSFP | 100000 | no data | no data | 0% | 0 |  | Project Ongoing
DOH CLCHD, ONE COVID 19 Allowance | CSFP | 23143281.25 | no data | no data | 100% | 23143281.25 |  | Fully Liquidated
DILG RO3 2022 SGLG Awardee | CSFP | 7000000 | no data | no data | 0% | 0 |  | Project Ongoing
DOLE-DILEEP | CSFP | 1250000 | no data | no data | 18.79% | 234867 |  | Project Ongoing
LGSF-Support to the Barangay Development Program of the National Task Force to End Local Communist Armed Conflict | CSFP | 13213764.34 | no data | no data | 0% | 0 |  | Project Ongoing
SM Primeholdings-Rehabilitation of Telabastagan Creek | Telabastagan, CSFP | 828023.34 | no data | no data | 100% | 828023.34 |  | Fully Liquidated
Province of Pampanga-Purchase of Service Vehicle (SP) | CSFP | 1400000 | no data | no data | 100% | 1400000 |  | Fully Liquidated
DILG RO III-Bottom Up Budgeting for Disaster Preparedness | different barangays of CSFP | 2250000 | no data | no data | 100% | 2250000 |  | Fully Liquidated
|  | 250000 | no data | no data | 100% | 250000 |  | Fully Liquidated
Presidential Management Staff (various projects of CSFP) | different barangays of CSFP | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
|  | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
|  | 1000000 | 2006 | 2007 | 100% | 1000000 |  | Fully Liquidated
|  | 1000000 | 2007 | 2007 | 100% | 1000000 |  | Fully Liquidated
DBM RO III - OPPSF | different barangays of CSFP | 50000000 | 2008 | 2008 | 100% | 50000000 |  | Fully Liquidated
|  | 15000000 | 2010 | 2010 | 100% | 15000000 |  | Fully Liquidated
North Luzon Railways, Corp. | San Nicolas to Telabastagan, CSFP | 27709118 | 2009 | 2010 | 100% | 27709118 |  | Fully Liquidated
DOLE RO III - DOLE Kabuhayan Nego Kart | different barangays of CSFP | 375000 | 2009-11-01 | 2010-02-01 | 100% | 375000 |  | Fully Liquidated
|  | 600000 | 2010-11-01 | 2011-02-01 | 100% | 600000 |  | Fully Liquidated
|  | 355000 | 2011-05-01 | 2011-08-01 | 100% | 355000 |  | Fully Liquidated
DOLE RO III - DOLE Integrated Livelihood Program | different barangays of CSFP | 200000 | 2011-04-01 | 2011-06-01 | 100% | 200000 |  | Fully Liquidated
DILG RO III - Public Transport Assistance Program | different barangays of CSFP | 368250 | no data | no data | 100% | 368250 |  | Fully Liquidated
DILG RO III - Gawad Pamana ng Lahi | different barangays of CSFP | 2000000 | 2012 | 2013 | 100% | 2000000 |  | Fully Liquidated
|  | 3000000 | Dec. 3, 2013 | Jan. 21, 2014 | 100% | 3000000 |  | Fully Liquidated
DBM RO III - Rehabilitation /Completion of road network of Regional Center at Maimpis CSFP | Maimpis, CSFP | 10000000 | no data | no data | 100% | 10000000 |  | Fully Liquidated
DBM RO III - Rehabilitation /Improvement of Maimpis Creek | Maimpis, CSFP | 10000000 | Oct. 16, 2012 | Nov. 23, 2012 | 100% | 10000000 |  | Fully Liquidated
DBM RO III - Asphalt Overlay/Asphalting of Pavement at Poblacion CSFP | Sto. Rosario, CSFP | 15000000 | no data | no data | 100% | 15000000 |  | Fully Liquidated
DBM RO III - Construction of Two-Storey Fire Department Building | Sto. Rosario, CSFP | 5000000 | Mar. 31, 2012 | June 27, 2012 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Parian Barangay Road, Mexico, Pampanga | Mexico, Pampanga | 5000000 | Dec. 7, 2012 | Feb. 5, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Brgy Sto. Niño & Moras, Sto. Tomas, Pampanga | Sto. Tomas, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Maniago Barangay Road, Minalin, Pampanga | Minalin, Pampanga | 5000000 | Dec. 26, 2012 | Feb. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Balucuc Tabuyuc Road, Apalit, Pampanga | Apalit, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Cabetican Barangay Road, Bacolor, Pampanga | Bacolor, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at San Pedro 2 Brgy Road to Brgy Sta. Lucia, Magalang, Pampanga | Magalang, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Sta. Ana Municipal Road, Pampanga | Sta. Ana, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at San Simon Municipal Road, Pampanga | San Simon, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Sasmuan Municipal Road, Pampanga | Sasmuan, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Concreting of Road at Arayat Municipal Road, Pampanga | Arayat, Pampanga | 5000000 | Nov. 23, 2012 | Jan. 22, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III - Rehabilitation of Balimbing-Del Carmen Creek | Del Carmen, CSFP | 20000000 | July 10, 2012 | Dec. 7, 2012 | 100% | 20000000 |  | Fully Liquidated
DSWD RO III - Papsmear Project for Women and Mothers of CSFP | different barangays of CSFP | 300000 | no data | no data | 100% | 300000 |  | Fully Liquidated
DBM RO III (Sen. Francis Escudero) - Repair and Rehabilitation of Public Markets | Old Public Market, Del Pilar, CSFP | 500000 | Jan. 4, 2016 | Feb. 12, 2016 | 100% | 500000 |  | Fully Liquidated
DBM RO III ( Cong. Oscar S. Rodriguez) - Financial Assistance to various LGUs for the implementation of Social Services | different barangays of CSFP | 3500000 | no data | no data | 100% | 3500000 |  | Fully Liquidated
DOST RO III - Upgrading of MRF | Del Pilar, CSFP | 170000 | no data | no data | 100% | 170000 |  | Fully Liquidated
DSWD RO III - Improvement of San Pablo Batic Day Care Center funded by BCDA | San Pablo DCC, CSFP | 200000 | Jan. 31, 2018 | Mar. 1, 2018 | 100% | 200000 |  | Fully Liquidated
DSWD RO III-Social Pension for Indigent Senior Citizens (BUB) | different barangays of CSFP | 499800 | 2014-01-01 | 2014-06-01 | 100% | 499800 |  | Fully Liquidated
DA RO III - Grassroots Participatory Budgeting Process - GPBP | different barangays of CSFP | 1000100 | no data | no data | 100% | 1000100 |  | Fully Liquidated
DOLE RO III - Yes Program | City College, CSFP | 100000 | no data | no data | 100% | 100000 |  | Fully Liquidated
DBM RO III (Sen. Teofisto Guingona III) - Construction of City College Building Elevator | City College, CSFP | 5000000 | Feb. 25, 2013 | Mar.27, 2013 | 100% | 5000000 |  | Fully Liquidated
DBM RO III (Sen. Francis Pangilinan) - Scholarship Program | City College, CSFP | 1000000 | no data | no data | 100% | 1000000 |  | Fully Liquidated
DBM RO III (Sen. Francis Pangilinan) - Priority Development Program | City College, CSFP | 500000 | no data | no data | 100% | 500000 |  | Fully Liquidated
DSWD RO III - Katas ng VAT Project | different barangays of CSFP | 1306000 | 2011-01-01 | May 23, 2011 | 100% | 1306000 |  | Fully Liquidated
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
signed |  |  | signed |  |  | signed
RIZZEL Y. MANGILIT |  |  | JOSE TIBURCIO S. CANLAS |  |  | Hon. VILMA B. CALUAG
Local Budget Officer |  |  | Local Accountant |  |  | Local Chief Executive
Note on I14: CACCO-Bangs: waiting for credit notice (2/1/17)
Note on I19: CACCO-Bangs: with credit notice
Note on I20: CACCO-Bangs: with credit notice, check for refund still on hand (1/15/17)
Note on I23: CACCO-Bangs: with credit notice

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
38