## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION III - CENTRAL LUZON |  | CALENDAR YEAR: | 2024
PROVINCE: | PAMPANGA |  | QUARTER: | 3
CITY/MUNICIPALITY: | CITY OF SAN FERNANDO (Capital)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Street Lighting Project/Electrification Program | Citywide | 11366045.8 |  |  | 0% | 0 |  | 4TH QUARTER ALLOTMENT RELEASE
Construction of Ossuary/Niches at Himlayan Fernandino, Lara, CSFP | Lara | 15000000 |  |  | 99.91% | 14986281.32 |  | Completed
Primary Care Facilities | - | 10000000 |  |  | 50% | 5000000
Economic Development
Farm Mechanization Program | Different Barangays | 3500000 | 2024-07-01 | 2024-11-01 | 0% | 0 |  | Solar Powered Irrigation - waiting for NTP
Small Farm Mechanization Program | Different Barangays | 2500000 | 2024-07-01 | 2024-11-01 | 99.68% | 2491880 |  | Waiting for CAD validation of recipients.
Provision of irrigation Facilities | Different Barangays | 1000000 | 2024-07-01 | 2024-11-01 | 99.71% | 997068
Upgrading/provision of tools and equipmet for the maintenance unit (tree trimming, electrical works, waterways clean-up, carpentry works andothers) |  | 10000000 |  |  | 0% |  |  | 4TH QUARTER ALLOTMENT RELEASE
Enhance Productivity of Agricultural Land | Different Barangays | 2000000 | 2024-07-01 | 2024-11-01 | 93.42% | 1868381
Animal Dispersal | Different Barangays | 1000000 | 2024-07-01 | 2024-12-01 | 99.69% | 996918
Construction and/or Rehabilitation of Roads and Bridges
Improvement/Construction of Road at Alasas, City of San Fernando, Pampanga | Alasas | 3000000 | April 12, 2024 | August 9, 2024 | 99.72% | 2991734.56 |  | Completed
Improvement/Construction of Road at Bulaon, City of San Fernando, Pampanga | Bulaon | 3000000 | May 8, 2024 | June 16, 2024 | 99.73% | 2991974.58 |  | Completed
Improvement/Construction of Road at Calulut, City of San Fernando, Pampanga | Calulut | 3000000 | April 12, 2024 | June 30, 2024 | 99.74% | 2992075.88 |  | Completed
Improvement/Construction of Road at Del Pilar, City of San Fernando, Pampanga | Del Pilar | 3000000 | May 2, 2024 | July 20, 2024 | 99.72% | 2991735.99 |  | Completed
Improvement/Construction of Road at Dela Paz Sur, City of San Fernando, Pampanga | Dela Paz Sur | 3000000 | May 20, 2024 | August 7, 2024 | 99.76% | 2992704.9 |  | Completed
Improvement/Construction of Road at Dolores, City of San Fernando, Pampanga | Dolores | 1045344.84 | August 21, 2024 | October 14, 2024 | 94.02% | 982827.52 |  | Completed
Improvement/Construction of Road at Lara, City of San Fernando, Pampanga | Lara | 3000000 | May 20, 2024 | July 08, 2024 | 99.64% | 2989088.91 |  | Completed
Improvement/Construction of Road at Magliman, City of San Fernando, Pampanga | Magliman | 3000000 | May 20, 2024 | September 16, 2024 | 99.67% | 2989965.18 |  | Completed
Improvement/Construction of Road at Maimpis, City of San Fernando, Pampanga | Maimpis | 3000000 | July 3, 2024 | July 25, 2024 | 99.66% | 2989735.19 |  | Completed
Improvement/Construction of Road at Malino, City of San Fernando, Pampanga | Malino | 3000000 | May 12, 2024 | July 30, 2024 | 99.71% | 2991338.25 |  | Completed
Improvement/Construction of Road at Panipuan, City of San Fernando, Pampanga | Panipuan | 3000000 |  |  | 0% | 0 |  | No notice to proceed
Improvement/Construction of Road at Quebiawan, City of San Fernando, Pampanga | Quebiawan | 3000000 | June 27, 2024 | August 25, 2025 | 99.76% | 2992769.93 |  | Completed
Improvement/Construction of Road at Saguin, City of San Fernando, Pampanga | Saguin | 3000000 | May 26, 2024 | August 13, 2024 | 99.69% | 2990550.58 |  | Completed
Improvement/Construction of Road at San Agustin, City of San Fernando, Pampanga | San Agustin | 3000000 | May 8, 2024 | June 16, 2024 | 99.7% | 2990989.99 |  | Completed
Improvement/Construction of Road at San Isidro, City of San Fernando, Pampanga | San Isidro | 3000000 | June 27, 2024 | August 5, 2024 | 99.74% | 2992079.35 |  | Completed
Improvement/Construction of Road at San Jose, City of San Fernando, Pampanga | San Jose | 3000000 | July 20, 2024 | October 7, 2004 | 99.77% | 2993080.95 |  | No notice to proceed
Improvement/Construction of Road at San Juan, City of San Fernando, Pampanga | San Juan | 3000000 | July 22, 2024 | October 9, 2004 | 99.71% | 2991179.75 |  | No notice to proceed
Improvement/Construction of Road at San Nicolas, City of San Fernando, Pampanga | San Nicolas | 3000000 | June 25, 2024 | September 12, 2024 | 99.69% | 2990745.99 |  | Completed
Improvement/Construction of Road at San Pedro, City of San Fernando, Pampanga | San Pedro | 3000000 |  |  | 0% | 0 |  | No notice to proceed
Improvement/Construction of Road at Sindalan, City of San Fernando, Pampanga | Sindalan | 3000000 | July 4, 2024 | September 21, 2024 | 99.7% | 2991101.63 |  | Completed
Improvement/Construction of Road at Sta. Lucia, City of San Fernando, Pampanga | Sta. Lucia | 3000000 | June 27, 2024 | October 4, 2024 | 99.72% | 2991482.68 |  | Completed
Improvement/Construction of Road at Sto. Nino, City of San Fernando, Pampanga | Sto. Nino | 3000000 | June 27, 2024 | October 4, 2024 | 99.72% | 2991562.06 |  | Completed
Improvement/Construction of Road at Pulung Bulu, City of San Fernando, Pampanga | Pulung Bulu | 3000000 |  |  | 0% | 0 |  | No notice to proceed
Improvement/Construction of Road at Telabastagan, City of San Fernando, Pampanga | Telabastagan | 3000000 | July 25, 2024 | October 12, 2024 | 99.71% | 2991196.03 |  | No notice to proceed
Aid to Barangay
Brgy. Alasas, CSFP
Rehabilitation / Construction of Lined Canal at Purok 1 | Brgy. Alasas, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Baliti, CSFP
Declogging & Cleaning of Canals, Manholes from Purok 1 to 7 | Brgy. Baliti, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Bulaon, CSP
Clearing and Decloggging of Lined Canal | Brgy. Bulaon, CSP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Calulut, CSFP
Rehabilitation of Line Canals in Northville 14 | Brgy. Calulut, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Del Carmen, CSFP
Installation of CCTV within Barangay | Brgy. Del Carmen, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Del Pilar, CSFP
Installation/rehabilitation of Street lighting System in Unisite Subdivision | Brgy. Del Pilar, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Del Rosario, CSFP
Concreting of Barangay Road at Purok 4 | Brgy. Del Rosario, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Dela Paz Norte, CSFP
Concreting of Road at Purok 7 | Brgy. Dela Paz Norte, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Dela Paz Sur, CSFP
Rehabilitation of Drainage System Lined canal at Purok 1 | Brgy. Dela Paz Sur, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Dolores, CSFP
Installation of CCTV And Public Address at Sitio Macabakle | Brgy. Dolores, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Juliana, CSFP
Fabrication/construction/installation of canal covers in Purok 5 | Brgy. Juliana, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Lara, CSFP
Rehabilitation of Health Center Located at Purok 6 | Brgy. Lara, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Lourdes, CSFP
Installation of CCTV & Public Address within the Barangay | Brgy. Lourdes, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Magliman, CSFP
Upgrading of CCTV at Purok 3 & 4 | Brgy. Magliman, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Maimpis, CSFP
Rehabilitation of canal at Juan Luna St Purok 6 | Brgy. Maimpis, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Malino, CSFP
Installation of Additional CCTVs located within Barangay | Brgy. Malino, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Malpitic, CSFP
Construction of Drainage System Line Canal with Cover | Brgy. Malpitic, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Pandaras, CSFP
Installation of Streetlights (Lamp Post) | Brgy. Pandaras, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Panipuan, CSFP
Repair/Rehabilitation of Line Canal Located in Purok 7 | Brgy. Panipuan, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Pulung Bulu, CSFP
Installation of Closed-Circuit Television (CCTV) within Barangay | Brgy. Pulung Bulu, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Quebiawan CSFP
Construction/Rehabilitation of Lined Canal at Purol 1, 2, 3, & 4 | Brgy. Quebiawan CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Saguin, CSFP
Construction of Line Canal at Purok 2 | Brgy. Saguin, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. San Agustin, CSFP
Rehabilitation of Line Canal At Greenhill's Village Brgy. San Agustin | Brgy. San Agustin, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. San Felipe, CSFP
Construction/Rehabilitation of Drainage System Lined canal with Cover at Purok 5 | Brgy. San Felipe, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. San Isidro, CSFP
Installation of Street LED Lights | Brgy. San Isidro, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. San Jose, CSFP
Completion of Multi-Purpose Hall Purok 5 | Brgy. San Jose, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. San Juan, CSFP
Installation of Streelights (LED Lights) in all Purok | Brgy. San Juan, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. San Nicolas, CSFP
Repair and Maintenance of Streetlights in all Sitios | Brgy. San Nicolas, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. San Pedro, CSFP
Installation of Streetlights at Purok 6 | Brgy. San Pedro, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Sta. Lucia, CSFP
Repair and Rehabilitation of Drainage System Line Canal at Purok 14 | Brgy. Sta. Lucia, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Santa Teresita, CSFP
Desilting and declogging at Purok 1, 2 & 3 | Brgy. Santa Teresita, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Sto. NIño, CSFP
Construction of Lined Canal at Saturn St. San Fernando Subdivision | Brgy. Sto. NIño, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Sto. Rosario, CSFP
Installation of Solar Streetlights | Brgy. Sto. Rosario, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Brgy. Sindalan, CSFP
Rehabilitation and Improvement of Public Park at Sindalan Sports Complex | Brgy. Sindalan, CSFP | 200000 | October 2024 | December 2024 | 100% | 200000 |  | Completed
Brgy. Telabastagan, CSFP
Construction of Drainage System Lined canal with Cover at Sitio San Pablo | Brgy. Telabastagan, CSFP | 200000 | October 2024 | December 2024 | 0% | 0 |  | Not yet started
Loan Amortization |  | 75000000 |  |  | 71.69% | 53767348.74 |  | ON-GOING
Environmental Management (pls list down specific projects)
Effective Garbage Collections & Disposal System | Motorpool Compound, Del Pilar | 12000000 | - | - | 0% | 0 |  | For PR 4th Quarter
Improvement of the Central Materials Recovery Facility - (Construction and Rehabilitation of Road) | CMRF, Lara | 10000000 | - | - | 0% | 0 |  | For PR 4th Quarter
Flood Control
Construction/Improvement of Lined Canal at Dolores, City of San Fernando, Pampanga | Dolores | 2000000 | June 27, 2024 | September 14, 2024 | 99.45% | 1988949.45 |  | Completed
Construction/Improvement of Lined Canal at Baliti, City of San Fernando, Pampanga | Baliti | 2000000 | May 20, 2024 | August 17, 2024 | 99.52% | 1990308.79 |  | Completed
Construction/Improvement of Lined Canal at Juliana, City of San Fernando, Pampanga | Juliana | 2000000 | April 12, 2024 | July 10, 2024 | 99.59% | 1991712.05 |  | Completed
Construction/Improvement of Lined Canal at Lourdes, City of San Fernando, Pampanga | Lourdes | 2000000 | June 27, 2024 | September 24, 2024 | 99.58% | 1991669.65 |  | Completed
Construction/Improvement of Lined Canal at San Pedro, City of San Fernando, Pampanga | San Pedro | 2000000 | May 25, 2024 | August 12, 2024 | 99.59% | 1991785.49 |  | Completed
Construction/ Improvement of Lined Canal at Sampaloc, Dolores, City of San Fernando, Pampanga | Dolores | 5000000 | June 25, 2024 | November 21, 2024 | 99.58% | 4979100 |  | Completed
Construction of Slope Protection at Del Carmen, City of San Fernando, Pampanga | Del Carmen | 3000000 | May 2, 2024 | July 30, 2024 | 99.68% | 2990361.64 |  | Completed
TOTAL |  | 248411390.64 |  |  |  | 160441684.03
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| (SIGNED) |  |  |  | (SIGNED)
| RIZZEL Y. MANGILIT |  |  |  | HON. VILMA B. CALUAG
| City Budget Officer |  |  |  | City Mayor
Note on A64: CACCO: Payment for the Financial Assistance for the Construction of Line Canal With Cover at Sitio Dungan at Barangay Del Carmen, City of San Fernando
Note on A84: CACCO: Payment for the Financial Assistance for the Rehabilitation/Repair of Canal with cover in Purok 2 St., Claire Subdivision, Barangay Maimpis, City of San Fernando, Pampanga
Note on A92: CACCO: Payment for the Financial Assistance for Road Concreting Located at Purok 1 Barangay Panipuan, City of San Fernando, Pampanga
Note on A98: CACCO: Payment for the Financial Assistance for the Additional Installation of Public Address System at Barangay Saguin, City of San Fernando, Pampanga
Note on A102: CACCO: Payment for the Financial Assistance for the Installation of CCTV at Barangay San Felipe, City of San Fernando, Pampanga
Note on A110: CACCO: Payment for the Financial Assistance for Desilting and Declogging of Canals within the Area of Barangay San Nicolas , City of San Fernando, Pampanga
Note on A118: CACCO: Payment for the Financial Assistance for the Construction of Line Canals and Concreting Road at Jupiter St., at Barangay Sto. Nino, City of San Fernando, Pampanga

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2